## Team Assignments
EGN 4950C Group 16 — Team Assignments (updated Apr 9, 2026)
Member | Section # | Area | Status
Kheiven D'Haiti (KD) kdhaiti2024@fau.edu
| 1.1 | Background Subtraction Tuning | Done ✅
| 1.3 | CDnet foreground coverage benchmark | Done ✅
| 2.1 | --mode CLI argument integration | Done ✅
| 2.2 | Super-Resolution Enhancement Module | Done ✅
| 2.4 | Data Integrity Validation (frame-level test) | Done ✅
| 2.6 | GUI Dashboard — Flask app, SSE, all API endpoints | Done ✅
| 2.6 | GUI Regression Tests + API Integration Tests | Open 🔲
| 3.1 | AES-256 encryption — initial CBC implementation | Done ✅
| 3.5 | demo.sh one-click launcher | Done ✅
| 3.6 | Final Report (docs/final_report.md) | Open 🔲
| 3.7 | Repository Polish + Documentation | Open 🔲
| 3.8 | Capstone Presentation (team lead) | Open 🔲
Riley Roberts (RR) robertsr2022@fau.edu
| 2.1 | Mode 2 & Mode 3 implementation | Open 🔲
| 2.1 | ModeDecision dispatch + mode1 gating (modes.py) | Done ✅
| 2.1 | Extend test_pipeline.py (enhance/encrypt/stop) | Open 🔲
| 2.1 | run_demo.py end-to-end on real footage | Open 🔲
| 2.5 | Algorithm comparison notebook (MOG2 vs KNN) | Open 🔲
| 2.5 | Stress test (test_pipeline_stress.py) | Open 🔲
| 2.6 | DemoMetadataWriter + renderer + split-screen | Done ✅
| 3.5 | Confirm webcam/IP camera real-time input | Open 🔲
| 3.6 | Final benchmarks notebook (final_results.ipynb) | Open 🔲
Victor De Souza Teixeira (VT) vdesouzateix2023@fau.edu
| 1.3 | PSNR, SSIM, compression ratio metrics | Done ✅
| 1.3 | milestone1_benchmark.ipynb | Done ✅
| 2.4 | CI integration (tests/test_data_integrity.py) | Open 🔲
| 3.1 | Upgrade AES-256-CBC to AES-256-GCM (auth tag) | Open 🔲
| 3.1 | IV + salt storage in DB per segment | Open 🔲
| 3.1 | Password-protected incident clip export | Open 🔲
| 3.1 | Encrypt/decrypt round-trip unit tests | Open 🔲
| 3.4 | Deployment packaging research (Docker/PyInstaller) | Open 🔲
Ashleyn Montano (AM) amontano2023@fau.edu
| 1.4 | SQLite schema, WAL mode, idx_cam_time index | Done ✅
| 1.4 | insert_segment() + camera/time queries | Done ✅
| 1.4 | Unit tests: database (20 tests) | Done ✅
| 2.3 | Add object_type field + extend insert_segment() | Open 🔲
| 2.3 | query_by_type() + daily storage summary CLI | Open 🔲
| 2.3 | Unit tests for new queries and CLI tool | Open 🔲
| 2.7 | Detection Tuning — MOG2/KNN calibration (w/ JS) | Open 🔲
| 3.2 | Searchable metadata index + stable API | Open 🔲
| 3.2 | Full-text / tag search + README docs | Open 🔲
Jorge Sanchez (JS) jorgesanchez2022@fau.edu
| 1.2 | ROI encoding — FFmpeg stdin pipe, dual-CRF | Done ✅
| 1.2 | Integration tests for ROI encoder (18 tests) | Done ✅
| 2.5 | Algorithm comparison notebook + recommendation doc | Open 🔲
| 2.5 | Stress test + memory bounds + storage extrapolation | Open 🔲
| 2.7 | Detection Tuning — calibration research (w/ AM) | Open 🔲
| 3.3 | Watchfolder daemon / external footage ingestion | Open 🔲
| 3.3 | Body camera / multi-source input support | Open 🔲

## Planner Tasks
EGN4950C Group 16 — Planner Tasks (Updated Apr 9, 2026 — post Audit + feat/mode-system merge)
Task Name | Bucket | Assigned To | Due Date | Priority | Milestone | Status | Notes
MILESTONE 1 — COMPLETED (all 19 tasks passing, tagged v0.1.0 on 2026-03-29)
Tune MOG2 parameters (night_mode, CLAHE, varThreshold) | Done | kdhaiti2024@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | night_mode flag; VAR_THRESHOLD_DAY=16/NIGHT=30; CLAHE preprocessing
Tune KNN parameters; compare with MOG2 on 46 CDnet scenes | Done | kdhaiti2024@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | Full CDnet sweep; MOG2 recommended as primary; results in outputs/cdnet_batch_results.log
Morphological cleanup (erosion/dilation) to remove mask noise | Done | kdhaiti2024@fau.edu | 2026-03-29T23:59:59Z | Medium | Milestone 1 | Done | MORPH_CLOSE + MORPH_OPEN with elliptical kernel; morph_kernel_size param exposed
Minimum contour area filter for small detections | Done | kdhaiti2024@fau.edu | 2026-03-29T23:59:59Z | Medium | Milestone 1 | Done | min_area param (default 500px); docstring notes 1500-2000px for HD footage
Unit tests: background subtraction (mask gen, edge cases, night mode) | Done | kdhaiti2024@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | tests/test_background_subtraction.py — 29 tests passing
Implement encode_segment() — pipe numpy frames to FFmpeg via stdin | Done | jorgesanchez2022@fau.edu | 2026-03-29T23:59:59Z | Urgent | Milestone 1 | Done | src/compression/roi_encoder.py; uses communicate() to avoid pipe deadlock
Dual-pass CRF encoding: foreground CRF 18, background CRF 45 | Done | jorgesanchez2022@fau.edu | 2026-03-29T23:59:59Z | Urgent | Milestone 1 | Done | has_targets flag selects foreground_crf vs background_crf in encode_segment()
Validate output is valid playable MP4 (not corrupted) | Done | jorgesanchez2022@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | Raises RuntimeError if output file missing or zero bytes after FFmpeg
Implement get_file_size() and log pre/post compression sizes | Done | jorgesanchez2022@fau.edu | 2026-03-29T23:59:59Z | Medium | Milestone 1 | Done | Returns bytes or 0 for missing file; logged per segment
Integration tests for ROI encoder (18 tests) | Done | jorgesanchez2022@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | tests/test_roi_encoder.py — encode, CRF, DB row, error handling
Implement compute_psnr() and compute_ssim() | Done | vdesouzateix2023@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | src/utils/metrics.py; verified against known reference values
Implement compute_compression_ratio() | Done | vdesouzateix2023@fau.edu | 2026-03-29T23:59:59Z | Medium | Milestone 1 | Done | src/utils/metrics.py; handles zero/negative inputs correctly
CDnet foreground coverage benchmark across all 46 scenes | Done | kdhaiti2024@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | scripts/run_all_cdnet.py; per-category avg FG% in outputs/cdnet_batch_results.log
Create notebooks/milestone1_benchmark.ipynb | Done | vdesouzateix2023@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | Runs pipeline on test clip, reports PSNR, SSIM, compression ratio
Document results in docs/milestone1_results.md | Done | vdesouzateix2023@fau.edu | 2026-03-29T23:59:59Z | Medium | Milestone 1 | Done | Compression ratio, PSNR, SSIM results documented
Create SQLite segments schema (db.py) with WAL mode and index | Done | amontano2023@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | WAL mode, idx_cam_time index, type hints, SegmentRow alias
Integrate DB writes into pipeline (one row per encoded segment) | Done | amontano2023@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | insert_segment() called in encode_segment() after every successful encode
Query: all segments from camera X with targets in last N hours | Done | amontano2023@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | query_recent_targets(camera_id, hours, db_path) — ORDER BY timestamp DESC
Unit tests: database (20 tests — WAL, index, multi-camera, edge cases) | Done | amontano2023@fau.edu | 2026-03-29T23:59:59Z | Important | Milestone 1 | Done | tests/test_database.py — expanded from 2 to 20 tests
MILESTONE 2 — NEW TASKS (added from Sponsor Meeting 2, Apr 1) • Due Apr 13
Implement Mode 2: store one background keyframe + per-frame object patches | Milestone 2 | robertsr2022@fau.edu | 2026-04-11T23:59:59Z | Urgent | Milestone 2 | Not Started | NEW from meeting. Background frame captured before motion; only moving-object bounding-box crops saved per frame. Best for low-traffic scenes. See meeting notes for Riley's description.
Implement Mode 3: object-only forensic mode (no background, padded crop only) | Milestone 2 | robertsr2022@fau.edu | 2026-04-11T23:59:59Z | Urgent | Milestone 2 | Not Started | NEW from meeting. Most aggressive mode — saves ONLY padded bounding-box crop around detected subject, zero background. Maximum data density. Use case: facial recognition pipeline.
Add demo/concat mode: stitch all output segments into single playback file | Milestone 2 | robertsr2022@fau.edu | 2026-04-10T23:59:59Z | Important | Milestone 2 | Not Started | NEW from meeting. Riley proposed a mode that concatenates segments so you can review full output without opening each 60-second clip individually.
Add object_type tag to DB schema (person, vehicle, cyclist, unknown) | Milestone 2 | amontano2023@fau.edu | 2026-04-10T23:59:59Z | Important | Milestone 2 | Not Started | NEW from meeting. Sponsor requires ability to search by subject type. Extend SegmentRow and insert_segment() to accept object_type field. Tie into BackgroundSubtractor region detection.
Zero data loss validation: automated frame-level comparison test | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Urgent | Milestone 2 | Done | tests/test_data_integrity.py — frame-level ROI pixel comparison; pass/fail logged per region
MILESTONE 2 — EXISTING TASKS • Due Apr 13
Research Real-ESRGAN CPU inference setup; document model download in DEV.md | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Important | Milestone 2 | Done | Documented in DEV.md; model files in models/ (gitignored); basicsr build issues on Py3.14 noted
Implement Enhancer.upscale_frame() using Real-ESRGAN / dnn_superres / bicubic | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Urgent | Milestone 2 | Done | src/enhancement/enhancer.py; three backends: dnn_superres, realesrgan, bicubic (always available)
Implement Enhancer.upscale_roi(frame, bbox) — upscale only bounding region | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Important | Milestone 2 | Done | Crops ROI, upscales, resizes back to original bbox dims, pastes in-place; shape preserved
Integrate enhancement into pipeline as optional post-offload pass (--enhance flag) | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Urgent | Milestone 2 | Done | --enhance / --enhance-model / --enhance-scale; bicubic fallback if model unavailable; enhance_batch() at segment encode
Benchmark enhancement processing time per frame on CPU hardware | Milestone 2 | kdhaiti2024@fau.edu | 2026-04-07T23:59:59Z | Medium | Milestone 2 | Not Started | Target hardware: Raspberry Pi or equivalent low-spec x86. Sponsor confirmed government hardware is not high-spec.
Write unit tests for Enhancer (output dimensions, bbox validation, is_available()) | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Important | Milestone 2 | Done | tests/test_enhancer.py; verified upscale_frame x2/x4, upscale_roi paste, enhance_batch, graceful unavailable
Create notebooks/algorithm_comparison.ipynb with side-by-side visualizations | Milestone 2 | jorgesanchez2022@fau.edu | 2026-04-08T23:59:59Z | Important | Milestone 2 | Not Started | MOG2 vs KNN side-by-side; data already collected in cdnet_batch_results.log
Write docs/algorithm_comparison.md — production recommendation | Milestone 2 | jorgesanchez2022@fau.edu | 2026-04-08T23:59:59Z | Medium | Milestone 2 | Not Started | Data ready in session_log_2026-03-26.md; recommendation is MOG2 as primary
Write tests/test_pipeline_stress.py — 1 hour simulated footage | Milestone 2 | jorgesanchez2022@fau.edu | 2026-04-09T23:59:59Z | Important | Milestone 2 | Not Started | Loop a test clip to simulate 1 hour of continuous operation
Verify memory does not grow unbounded over 1 hour of operation | Milestone 2 | jorgesanchez2022@fau.edu | 2026-04-09T23:59:59Z | Important | Milestone 2 | Not Started | Use tracemalloc or psutil to monitor RSS over time
Extrapolate 1-hour results to estimate storage for 60-day retention (100 cameras) | Milestone 2 | jorgesanchez2022@fau.edu | 2026-04-10T23:59:59Z | Medium | Milestone 2 | Not Started | Sponsor requirement: 60 days of recording on 100+ camera systems. Document in docs/stress_test_results.md
Document stress test findings in docs/stress_test_results.md | Milestone 2 | jorgesanchez2022@fau.edu | 2026-04-11T23:59:59Z | Medium | Milestone 2 | Not Started | Include: runtime, peak memory, projected weekly/60-day storage per camera, Mode 0 vs Mode 1 comparison
Add CLI query tool: db_query.py --camera cam_01 --last-hours 24 --type person | Milestone 2 | amontano2023@fau.edu | 2026-04-13T23:59:59Z | Medium | Milestone 2 | Not Started | Updated from original — add --type filter to support new object_type DB field
MILESTONE 2 — AUDIT TASKS (added Apr 9, 2026 from pre-merge audit) • Due Apr 18
Mode dispatch system: modes.py (ModeDecision, validate_mode, get_mode_decision) + pipeline.py dispatch | Done | robertsr2022@fau.edu | 2026-04-09T23:59:59Z | Urgent | Milestone 2 | Done | PR #6 feat/mode-system merged. modes.py fully tested. pipeline.py uses get_mode_decision() per frame.
Mode1 frame-gating unit tests (test_pipeline.py: EOF-boundary + mode1 event-filter) | Done | robertsr2022@fau.edu | 2026-04-09T23:59:59Z | Important | Milestone 2 | Done | tests/test_pipeline.py — 2/2 passing. Covers exact-segment-boundary EOF and mode1 frame selection.
Demo metadata writer (DemoMetadataWriter) + JSONL sidecar per buffered frame | Done | robertsr2022@fau.edu | 2026-04-09T23:59:59Z | Important | Milestone 2 | Done | src/demo/demo_metadata.py — context manager; writes frame index, time, mode, segment, regions per frame.
Demo video renderer and split-screen compositor (demo.py, split_screen.py, run_demo.py) | Done | robertsr2022@fau.edu | 2026-04-09T23:59:59Z | Urgent | Milestone 2 | Done | src/demo/: render_demo(), build_split_screen_from_manifest(). 1–4 mode grid; frame-gap handling; ROI overlays.
Upgrade encryption from AES-256-CBC to AES-256-GCM (authenticated encryption, audit finding) | Milestone 2 | vdesouzateix2023@fau.edu | 2026-04-18T23:59:59Z | Important | Milestone 2 | Not Started | CBC has no authentication tag — bit-flip attacks pass silently. GCM = authenticated encryption, drop-in via cryptography lib.
Extend test_pipeline.py: add tests for --enhance bicubic path, --encrypt round-trip, stop_event graceful shutdown | Milestone 2 | robertsr2022@fau.edu | 2026-04-18T23:59:59Z | Important | Milestone 2 | Not Started | Audit finding. Bicubic path needs test (no SR weights). Encrypt test: verify .enc written, .mp4 deleted. Stop-event: break mid-loop.
GUI regression tests for /api/start /api/stop /api/status /api/segments /api/storage | Milestone 2 | kdhaiti2024@fau.edu | 2026-04-18T23:59:59Z | Important | Milestone 2 | Not Started | Audit finding. Covers all 5 API endpoints. Assert HTTP status, JSON shape, and state transitions.
Run run_demo.py end-to-end on a real test clip — verify split-screen composite output | Milestone 2 | robertsr2022@fau.edu | 2026-04-18T23:59:59Z | Important | Milestone 2 | Not Started | Audit recommendation. python -m src.demo.run_demo --input data/test.mp4 --output outputs/ --camera-id cam_test
SSE Last-Event-ID resume + deque log history (audit fix — already committed in 6ec4ee2) | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Medium | Milestone 2 | Done | app.py: monotonic event IDs, Last-Event-ID backlog replay, collections.deque(maxlen=300). No duplicate lines on reconnect.
MILESTONE 2 — DETECTION TUNING TASKS (new section 2.7 — added Apr 9, 2026) • Due Apr 18
Research + calibrate MOG2/KNN params on base-entry footage (day, night, gate, walkway) | Milestone 2 | amontano2023@fau.edu; jorgesanchez2022@fau.edu | 2026-04-18T23:59:59Z | Important | Milestone 2 | Not Started | New section 2.7. Target: false-positive rate < 2% on static scenes. Compile docs/detection_tuning.md with optimal param sets per lighting condition.
Measure false positive / false negative rates across lighting conditions | Milestone 2 | amontano2023@fau.edu; jorgesanchez2022@fau.edu | 2026-04-18T23:59:59Z | Important | Milestone 2 | Not Started | Run both algorithms on representative footage. Document FP/FN rates. Goal: match or exceed sponsor baseline of ~6x reduction (YOLO walkway camera).
Update BackgroundSubtractor default parameters + write detection accuracy unit tests | Milestone 2 | amontano2023@fau.edu; jorgesanchez2022@fau.edu | 2026-04-18T23:59:59Z | Medium | Milestone 2 | Not Started | Commit recommended defaults to background_subtraction.py. Add tests/test_detection_tuning.py with ground-truth clips.
MILESTONE 3 — NEW TASKS (added from Sponsor Meeting 2, Apr 1) • Due May 1
Searchable metadata index: query segments by object type, camera, and time range | Milestone 3 | amontano2023@fau.edu | 2026-04-22T23:59:59Z | Urgent | Milestone 3 | Not Started | NEW from meeting. Sponsor requirement: eliminate manual video scrubbing. Expose query_by_type(object_type, camera_id, start_time, end_time). Return list of matching segment file paths.
Implement AES-256 encryption for compressed output video files (--encrypt flag) | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Urgent | Milestone 3 | Done | src/utils/encryption.py; AES-256-CBC; PBKDF2 600k iters; password or raw-key mode; IV+salt in header; integrated in pipeline.py
Add password-protected export for incident clips and reports | Milestone 3 | vdesouzateix2023@fau.edu | 2026-04-25T23:59:59Z | Important | Milestone 3 | Not Started | NEW from meeting. Sponsor showed existing commercial systems charge extra for this. Our system should include it by default. User supplies password; output clip is AES-encrypted zip or container.
Implement drag-and-drop video import interface for external footage | Milestone 3 | jorgesanchez2022@fau.edu | 2026-04-26T23:59:59Z | Medium | Milestone 3 | Not Started | NEW from meeting. Sponsor wants ability to feed in footage from external sources (e.g. body cameras, other systems). Watchfolder approach or simple CLI drop-folder that auto-ingests new video files.
Research and document deployment packaging format for government COTS deployment | Milestone 3 | vdesouzateix2023@fau.edu | 2026-04-20T23:59:59Z | Important | Milestone 3 | Not Started | NEW from meeting. Riley raised this question directly. Cody will follow up with Gina. Document findings: Docker, PyInstaller, OS package, or source tarball. Must be compatible with COTS x86 hardware.
Research AI-based compression alternative; benchmark vs current MOG2 approach | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Medium | Milestone 3 | Done | docs/ai_compression_research.md; YOLO detection overhead vs MOG2; neural codecs (NDAA); recommendation: MOG2 primary
MILESTONE 3 — EXISTING TASKS • Due May 1
Confirm pipeline runs on USB or IP camera input in real time | Milestone 3 | robertsr2022@fau.edu | 2026-04-14T23:59:59Z | Urgent | Milestone 3 | Not Started | Test with --input 0 (webcam) on target hardware; verify no frame drops
Add --preview flag to pipeline (live foreground mask + original feed) | Milestone 3 | robertsr2022@fau.edu | 2026-04-15T23:59:59Z | Important | Milestone 3 | Not Started | Already exists in argparse; verify cv2.imshow works on demo laptop
Create demo.sh — one-click pipeline launch with sensible defaults | Done | kdhaiti2024@fau.edu | 2026-04-09T23:59:59Z | Medium | Milestone 3 | Done | demo.sh in project root; launches run_gui.py with default port 5000; works headless or with browser auto-open
Test demo on laptop with no GPU (simulate target hardware) | Milestone 3 | robertsr2022@fau.edu | 2026-04-17T23:59:59Z | Urgent | Milestone 3 | Not Started | Must run on stock CPU-only machine — no CUDA dependency. Sponsor confirmed government hardware is low-spec.
Create docs/final_report.md — architecture, results, limitations | Milestone 3 | kdhaiti2024@fau.edu | 2026-04-18T23:59:59Z | Urgent | Milestone 3 | Not Started | Sections: system arch, mode descriptions (0-3), benchmark results, enhancement results, encryption design
Populate final numbers table: compression ratio, PSNR, SSIM, storage per day per camera | Milestone 3 | robertsr2022@fau.edu | 2026-04-19T23:59:59Z | Urgent | Milestone 3 | Not Started | Numbers must be reproducible by running notebooks/final_results.ipynb. Include Mode 0 and Mode 1 comparison.
Create notebooks/final_results.ipynb — re-run all benchmarks from scratch | Milestone 3 | robertsr2022@fau.edu | 2026-04-20T23:59:59Z | Important | Milestone 3 | Not Started | Must run end-to-end without errors on final codebase
Include side-by-side figure: original vs Mode 0 vs Mode 1 compressed frame | Milestone 3 | robertsr2022@fau.edu | 2026-04-21T23:59:59Z | Medium | Milestone 3 | Not Started | Add to final_report.md and final_results.ipynb
Ensure all public-facing modules have docstrings | Milestone 3 | kdhaiti2024@fau.edu | 2026-04-22T23:59:59Z | Medium | Milestone 3 | Not Started | Check: pipeline.py, roi_encoder.py, db.py, frame_source.py, metrics.py, enhancer.py
Update README.md to reflect final architecture and all four modes
Update DEV.md with any new setup steps discovered during development | Milestone 3 | kdhaiti2024@fau.edu | 2026-04-24T23:59:59Z | Medium | Milestone 3 | Not Started | Include: Real-ESRGAN model download, ffmpeg-python install, CDnet dataset setup, encryption deps
Ensure requirements.txt is accurate (pip freeze cross-check) | Milestone 3 | kdhaiti2024@fau.edu | 2026-04-25T23:59:59Z | Medium | Milestone 3 | Not Started | Run: pip freeze > requirements_check.txt and diff against requirements.txt
Tag final commit as v1.0.0 | Milestone 3 | kdhaiti2024@fau.edu | 2026-04-26T23:59:59Z | Important | Milestone 3 | Not Started | git tag v1.0.0 && git push origin v1.0.0
Verify repo clones cleanly on fresh machine and pipeline runs | Milestone 3 | kdhaiti2024@fau.edu | 2026-04-27T23:59:59Z | Urgent | Milestone 3 | Not Started | New team member should be able to run pipeline in under 15 min using README only
Create slide deck: problem, approach, modes, results, demo footage | Milestone 3 | All | 2026-04-28T23:59:59Z | Urgent | Milestone 3 | Not Started | Sections: problem statement (Cody's storage/scrubbing challenge), our approach, 4-mode system, benchmark numbers, live demo clip
Prepare 2-minute live demo segment | Milestone 3 | kdhaiti2024@fau.edu; robertsr2022@fau.edu | 2026-04-29T23:59:59Z | Urgent | Milestone 3 | Not Started | Show: camera feed, foreground mask, Mode 0 output, Mode 1 output, storage stats, metadata query
Rehearse full presentation as a team | Milestone 3 | All | 2026-04-30T23:59:59Z | Important | Milestone 3 | Not Started | All team members present
Submit final deliverable to course portal | Milestone 3 | All | 2026-05-01T23:59:59Z | Urgent | Milestone 3 | Not Started | Hard deadline: May 6, 2026
COLOR KEY ¦ Green = Done ¦ Orange = M2 New tasks ¦ Blue = M2 Existing tasks ¦ Light blue = Audit tasks (Apr 9) ¦ White = M3 tasks